## Sheet1
Name: Đoàn Anh Minh
| NO | TASK | DATE | ESTIMATE TIME | ACTUAL TIME
| 1 | Change Management Plan & Change request form | 14/10/2016
| 1.1 | Create new document | 14/10/2016 | 4 | 5
| 1.2 | Update data in Change Management Plan | 14/10/2016 | 2 | 2