## Sheet1
Name: Đoàn Anh Minh
| NO | TASK | DATE | ESTIMATE TIME | ACTUAL TIME
| 1 | Study Basic Nodejs | 17/10/2016 | 6 | 3
| 2 | Team Meeting with Mentor | 17/10/2016 | 1.5 | 1.5
| 3 | Read PSP document | 19/10/2016 | 2 | 2
| 4 | Read PSP document | 20/10/2016 | 2 | 3
| 5 | Team Meeting with Mentor | 21/10/2016 | 2 | 2
| 6 | Read Software Requirement Slide | 21/10/2016 | 2 | 1
| 7 | Team Meeting | 22/10/2016 | 3 | 3
| 6 | Change Management Plan and Change Request Form | 23/10/2016
| 6.1 | Fix the process, update data in Roles and Responsibilities board | 23/10/2016 | 1 | 1
| 6.2 | Update Template of Change Request Form Document | 23/10/2016 | 0.5 | 0.25